## Risk Assessment
RISK ASSESSMENT FOR HTT ACTIVE EQUIPMENT AUDIT
| Activity | Hazard | Risk | Consequence | Who is exposed | Existing Controls | Risk Evaluation |  |  |  | Additional Controls | Responsible Person | Risk Residue
[7 empty] | P | S | RV | RL |  |  | P | S | RV | RL
1 | Driving. ( Driving to and from site) | Vehicle road worthiness | Vehicle breakdown, Accidents, Damage to property. | Fatality, serious injury, Finacial Losses | Driver, passengers and Other Road users | All vehicles are roadworthly and licenced, Daily Vehicle Inspection checks, Weekly Vehicle safety Inspection checks. | 3 | 3 | 9 | H | Preventive, Corrective and Maintenance service as per GNC_IMS_HR_PRO_19-Vehicle/Equipment Maintenance procedure based on a schedule. | SHEQ Manager, Logistics officer. | 2 | 3 | 6 | M
|  | Vehicle/ trailer not fit for purpose | Cannot excute work properly, Accident, Damage to vehicle. | Fatality, serious injuries, Property damage | Driver, passengers and Other Road users | Ensure all vehicles are fit for purpose | 2 | 2 | 4 | M | Vehicle schedule for specific scope | Logistic officer/Driver | 1 | 2 | 2 | L
|  | Open load bin | Transport of people in the loadbins, Tools/Equipment theft on transit in the open loadbin | Fatality, serious injuries, Finacial Losses | Passengers on a loadbin | No transport of any party in load bins,Close load bins with tarpaulin. | 2 | 3 | 6 | M | Project kickoff meeting/Induction training to team members and adhere to GNC_IMS_SHEQ_PRO_14- Motor Vehicle driving procedure. | SHEQ Manager/ Project Manager | 1 | 3 | 3 | L
|  | Vehicles not fitted with IVMS | Driver behaviour monitoring; | Fatality, serious injuries, Equipment damage | Driver, passengers and Other Road users | Vehicle tracking device installed, Drivers behavior monitoring ,Consequence management and Violations action measures. | 2 | 2 | 4 | M | Awareness training during kickoff meeting on Occupational Road Risks in reference to GNC_IMS_SHEQ_PRO_14-Motor Vehicle Driving procedure. | SHEQ Manager/ Project Manager | 1 | 2 | 2 | L
|  | Theft or Hi-Jacking of Vehicle | Vehicle loss; Vehicle damages | Fatality, serious injury, Finacial Losses | Driver and passengers | Vehicle Insurance, Vehicle Tracking devices installed | 2 | 3 | 6 | M | Plan the journey and fill the GNC_IMS_SHEQ_F21-Journey Management plan, Regular checks of the vehicle condition during rest periods, Do not drive at night. | Project Manager/ Driver | 1 | 3 | 3 | L
|  | Unauthorised Driver / Operator | Driver not licensed, Accidents, Damage to property | Financial Losses; Reputational Damage; Fatality and Serious Injury | Driver, Passengers and other road users | Valid Driver's license, Driver competencies and training , Authorisation to operate specific vehicle ,Communiocation of GNC_IMS_SHEQ_POL_04-Driving policy. | 2 | 3 | 6 | M | Driver's behaviour records interpretation. | Project Manager/Logistic officer | 1 | 3 | 3 | L
|  | Driver Fatigue | Accidents, Damage to property | Financial Losses, Reputational Damage, Fatality and Serious Injury | Driver, Passengers and other road users | Adhere to GNC_IMS_SHEQ_PRO_14- Motor Vehicle driving procedure on resting periods in between the journey and Resting period before initiating a Journey. | 3 | 3 | 9 | H | Driver awareness training/induction, Follow Journey management plan rest periods, driver well hydrated | Project Manager/Logistic officer | 2 | 3 | 6 | M
|  | Not obeying HT Safety Rules | Accidents, Damage to property | Financial Losses, Reputational Damage; Fatality and Serious Injury | Driver, Passengers and other road users | Minimum resting periods between shifts ,Journey Management, Medical Fitness | 2 | 3 | 6 | M | Consequence management and Disciplinary action, Awareness Training. | SHEQ Manager/HR &Admin Manager | 1 | 3 | 3 | L
|  | Inclement Weather | Poor Road conditions and visibility, Accidents, Property, Environmental impacts | Property Damage, Fatality or Serious Injuries | Driver, Passengers and other road users | Discourage Occupational driving when weather is bad, Drive speed limits to match road condition | 3 | 3 | 9 | H | Induction training on reporting weather conditions and advise stopages as mitigations for the hazards as a result of bad weather. | Driver, Project Manager and Logistic officer | 1 | 3 | 3 | L
|  | Drivers Competence | Driver not licensed, Accidents, Damage to property | Financial Losses; Reputational Damage, Fatality and Serious Injury | Driver and passengers (Vehicle users) | Valid Driver's license, Driver competencies and training , Authorisation to operate specific vehicle ,Communiocation of GNC_IMS_SHEQ_POL_04-Driving policy. | 2 | 3 | 6 | M | Driver training need identification and Vehicle driving dashboard in place | SHEQ Manager/HR &Admin Manager | 1 | 3 | 3 | L
|  | Night Driving | Accidents, Damage to property | Financial Losses; Reputational Damage, Fatality and Serious Injury | Driver and passengers (Vehicle users) | No night driving allowed, Journey Management Plan followup | 2 | 3 | 6 | M | Plan the journey and fill the GNC_IMS_SHEQ_F21-Journey Management plan, Regular checks of the vehicle condition during rest periods, Do not drive at night. | Project Manager/ Driver | 1 | 3 | 3 | L
|  | Narrow road to access site (potholes, Cyclists and Pedestrians, Vehicles, Workzone with unpredictable changes) | _Blind corners, _Sharp turns, _Shoppers, _Vendors, _Kiosk | _Vehicle crash _traffic stuck due to barrier on the road | Pedestrians, other road users | Respect pedestrian and street vendors who may cross the narrow road at any time t. _Be aware of the surrounding: Its essential to take care and be aware of the surrounding to reduce risks of accident on the road | 2 | 3 | 6 | M | Keep the vehicle in top condition: make sure everything is working correctly from brakes to the engine, tyres and horn to ensure safe drive. NB: Remember that if the vehicle develops a mechanical problem on the way it will be extremely hard to fix whilst on the road | Site Supervisor/ Driver | 1 | 3 | 3 | L
|  | Vehicle not fitted with Emergency Equipment | Can not attend to injuries and fire, Property damage, Employee Health | Financial Losses, Infections | Driver and passengers | Fist Aid kit and Fire Extinghuiser available in vehicle, Weekly vehicle safety checks. | 2 | 2 | 4 | M | Fill Vehicle Safety inspection checklist before initiate a Journey | Project Manager/ Driver | 1 | 2 | 2 | L
2 | Ascending and Descending the tower for active equipment audit | Slips, Falls, suspended with harness at height, Material fall from height | Fatality, Injuries | Lost time Injuries, Business reputation | Riggers | Only competent personnel with valid Work at height certificates should climb the tower. Wear all necessary personal protective equipment (Safety helmet, reflective jacket, safety shoes) | 3 | 2 | 6 | M | Observe GNC_IMS_SHEQ_PRO_18-Work at Height procedure, use fall protection gears in complete form ie Body harness, Energy shock absorber lanyard and work positioning lanyard. No one should be located on a drop zone. | Riggers | 2 | 2 | 4 | M
3 | Tower Photo and measurement taking at work zone | Slips, Falls, trips suspended with harness at height, Material/ equipment fall from height | Injuries, Material Damage | Lost time | Riggers at height | Support all tools/ equipment with straps to avoid dropping. | 2 | 2 | 4 | M | Use the Work positioning lanyard when working at height to allow hand free on this operations (photo taking) | Site Supervisor to enforce during Daily Toolbox talk meetings | 1 | 2 | 2 | L
4 | Ground site activities and movement (Fire Hazards identification out of Fire breakout and Equipment audit) | Slips, trips and Fall _Fire effects on tower leg | Injuries _Structure damage | Lost time Injuries _Financial loss | All team members on the ground | There should not be any ground movements when work at height operations are in progress | 1 | 3 | 3 | L | Do a site ground inspection to establish open ducts, manholes or equipment not closed or broken door on equipment, fire damages. Avoid confronting by snake, do not touch a snake that appears to be dead, avoid walking onto spider web and contact with Bees, wasps | Site Supervisor/ Riggers | 1 | 3 | 3 | L

## Matrix
Risk Matrix
Probability / Likelihood | Consequence / Severity
| Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
Rare (1) | 1 | 2 | 3 | 4 | 5
Possible (2) | 2 | 4 | 6 | 8 | 10
Likely (3) | 3 | 6 | 9 | 12 | 15
Often (4) | 4 | 8 | 12 | 16 | 20
Frequent / Almost Certain (5) | 5 | 10 | 15 | 20 | 25
15-25 | Extreme Risk | Change to the Process shall be made to reduce the risk
8-12 | High Risk | Activity should be modified to include remeidal planning and action.
4-6 | Moderate Risk | Work activity can be performed subject to management/modification
1-3 | Low Risk | No action is Required unless escalation of risk is possible.

## Method Statement
METHOD STATEMENT - GNC Solutions Ltd
Client: HELIOS TOWERS TANZANIA
Date on-site start: September2024
Due Date on-site completion: November2024
Hours of work: 07:00am-17:00pm
Emergency contact : Project Manager: +255 763 477 700 HSE Manager: +255 759 002 649 | Emergency contact : Police Dar Es Salaam:- +255 689 387 638 Bochi Hospital:- +255 769 625 936 Fire-: +255 713 552 097
1. Description of the work | HTT ACTIVE EQUIPMENT AUDIT
Thorough check on the existing active equipments ( MW Dish, GSM Antenna, RRU’s, ODU’s and other types of RRU) on the tower to establish • Equipment Make/Model • Equipment Owner (Accurate - trace cable to tenant cabinet) • Equipment Status (Active/Inactive (no cable)) • Height from ground • Equipment Size • Azimuth • Feeder Cables (No. of and size) • Label each equipment per tenant colour and shape (where available) • Fill out Site Form / Digital input form with relevant information for each piece • of equipment • Ensure to take all necessary photos of equipment and other details. • Measurement accuracy and precision is required.
2. Description of site Location | 155 Sites
From : HTT
Name : Benjamin Michael
Collection of the information in for planning prior commencing the work. The provision of site specific information will assist in the planning and safe execution of the work. The informations will not eliminate the hazards but will help reduce the risks associated with the hazards
3. First Aid | First Aid Kit will be available on site at all time where work is in progress
First Aider will be Jonathan Meena, Baraka Mgoya, Leve Ndondwa and Edmund Frednand
GNC_IMS_SHEQ_F06-Incident Flash and Report form will be available in the site folder and shall be filled up for every incident occurence .Completed form must be submitted to GNC Solutions Ltd Head office for record keeping and Minor/Major investigation if recommended in the form/report.
4. Welfare | Village/Local Government leaders shall be notified of the team existance on the area, Drinking Water will be supplied to every staff on duty at site, Arrangement for getting lunch at site will be made to avoid Occupational driving of staff from site to the service centres. Neighbourhood toilet will be requested in advance for use just in case.
5. PPE requirements | PPE will be provided as follow: Safety Footwear, Personal Fall Protection Equipment (Fall Arrest Kit), Reflective/high visibility jackets, Safety glass/Goggles and Working gloves.
6. Sequence of work | Project Commencement: Ensure that a fully SHEQ site folder that contain relevant documets such as, RAMS are available on hand. Check to ensure that site access permit, keys are up to date before departing to site.
Assurance: Ensure the site access letter/permit in place, confirm all tools, equipment and materials are available and safe for use before departing to site.
Site Access for Equipment audit: Ensure the site is booked in upon attendance (ie NOC etc,,,), Inspect the site grounding and structural work, measure all equipments as per specification and record results for audit report.
Danger tape around site: Before conducting any site operations demarcate the site to prevent unwanted/unauthorized access.
WORKING AT HEIGHT FOR EQUIPMENT AUDIT: Fall-Arrest Harness System and the following procedures will be followed by our workers when working at height: 1) Qualification for our workers to work at height will include climber’s valid certification, medical fittness report/certificate. 2) Each anchor point must be located so that a lanyard can be attached before the person moves into a position that they may fall. 3) Access to work zone will be by a tower ladder. 4) No person is allowed to work at height alone. 5) Consider emergency plan/procedure should there be a fall to retrieve the suspended person.
Structure Pre-Check: Prior to commencing any structural work, Carryout structure inspection for issues/risks and ensure the structure is safe to work on.
Data collection: Equipment audit Exercise comprises of data collection where one personnel do write the results from measurements and photos that are taken during the audit as per specification for report writing.
NOTE: This works does not involve network outage, but incase it has to the approval must be secured from Operator/Helios Tower. This must be well known before deploying to site for site rectification works and only the approval will initiated when the work has reached at the height where the network outage needs to be executed.
7. Supervision arrangements and responsibilities | GNC Solutions Ltd Site supervisor will control all operations at site. All staff at site will be inducted, instructed and informed with regards to all works they are involved in and will be competent for the job.
Monitoring of all aspects of the works, processes and procedures will be undertaken by GNC Solutions Ltd Project Manager/Site Supervisor.
8. Equipment | Equipment to be used in this job (Equipment audit) will be Digital calliper, GPS device , Digital camera / Smartphone with zoom capability, Measuring tape (100m) and 5m steel tape measure, Notepad or digital tablet for recording measurements , Laptop for data transfer and storage, Compass , Board Markers & Pen and Cable tracing device for determining operator of equipment . Regular checking and maintenance of equipment such in order to minimize Environmental impacts.
List of vehicles T483DLP Hardbody Pick-up– GPS tracking system/Devices installed
9.Environmental Controls | 1. Use of Vehicles in relation to Air emission shall be controlled by a regular Vehicle Maintenance. 2. Generation of waste (plastic, cement bags) and disposal to meet Waste Management procedure requirements 3. Noise and Dust emissios will be kept to a minimum.
10. Emergency procedures | The site emergency preparedness and response plan will be issued at site during kick off meeting before commencing any work as follow:
Fire Emergency: If the fire can not be controlled with fire extinguisher on hand, evacuate the work area and proceed to the designated assembly point. Perform a count of personnel to ensure that everyone is at the assembly point. _Notify emergency services or fire department and give following information (Supervisor's name, company name, site location, direction to the site, nature and severity of the emergency and wait for and follow any instructions from the emergency services operator.)
Incase of a insect bite, sting or a snakebite the first Aider will go the following steps: 1. Wash to clean the affected area, remove the sting but not to squeeze the skin, do not suck by mouth, Obtain medical help As Soon As Possible
Fall Arrest rescue: If a Casualty is concious, uninjured and within reach of the structure, the rescuer can supply the casualty with a new shock absorber to climb back to safety. In the case a casualty being unable to climb back to safety, a rescue needs to be initiated. This may be accomplished through one rescue methods that typically involves attachment of the casualty to a rescue lifeline. Rescue Kit shall be located at a work zone/ area
Medical Emergencies If am medical emergeny ( Fall from height, Insect bite,etc ) Occurs on site _Perform medical treatment (e.g. ,CPR, Bandaging). _If Injuries are significant then notify emegency services or nearby ambulance service immediately by giving the operator a following information ( Supervisor's name, company name, site location, direction to the site, nature and severity of the emergency and wait for and follow any instructions from the emergency services operator and assist medical personnel in whatever safe manner they request)
GNC_IMS_SHEQ_F06-Incident flash and report form shall be written by the Site supervisor signed also by the first Aider immediately once the team had assure the injured safety by attended at a nearby hospital. All Incidents must be reported with in 24 Hours. The incident will be tracked and investigated.
This report must be conveyed to GNC Solutions Ltd SHEQ Manager immediately after completion. SHEQ Manager to report the same to HTT Project team and Manager, Health and Safety. Time frame for reporting shall be within 24Hrs from Incident occurrence.
11. Control of site operations
Work will not commence until everyone present has attended Toolbox meeting/induction at site and Personal Protective Equipment (PPE) has been worn by each personnel.Weather conditions such as heavy rain, lightning, strong winds will cause works to be terminated until an improvement in conditions. All Operators will work in a safe and healthy manner and cooperate with other personnel and the GNC Solutions Ltd has the Site Supervisor to ensure safe delivery of the work.

## Manning List
MANNING LIST (HTT ACTIVE EQUIPMENT AUDIT)
Team | SN | Name | Designation | Medical Fitness | Work at Height | Site
1 | 1 | CHARLES KOMBA | RIGGER | FIT | YES | 155 Sites
| 2 | EDMUND INNOCENT FREDNAND | SITE SUPERVISOR/ RIGGER/ FIRST AIDER | FIT | YES
| 3 | GIFTI MORI | RIGGER | FIT | YES
| 4 | JONATHAN JOHANSON MEENA | SITE SUPERVISOR/ RIGGER/ FIRST AIDER | FIT | YES
| 5 | LEVO AHAMADI NDONDWA | SITE SUPERVISOR/ RIGGER/ FIRST AIDER | FIT | YES
| 6 | ALLY JAMES | RIGGER | FIT | YES
| 7 | BARAKA SEBASTIAN MGOYA | SITE SUPERVISOR/ RIGGER/ FIRST AIDER | FIT | YES
| 8 | JULIUS NGALLO | RIGGER | FIT | YES
| 9 | MAJUTO LUBALE | RIGGER | FIT | YES
| 10 | SALEHE OMARY SALEHE | RIGGER | FIT | YES
| 11 | IBRAHIM KUNGUNI | DRIVER | FIT | NO
Prepared by: GNC Solutions Ltd |  |  | Signature: | Date: 24/09/2024
Name: |  | Michael Ngido
Designation: |  | SHEQ Manager
Reviewed and Approved by: GNC Solutions Ltd |  |  | Signature: | Date: 24/09/2024
Name: |  | Onesmo Swalo
Designation: |  | Project Manager
Approved by SHEQ Manager [Helios Towers] |  |  | Signature: | Date:
Name: |  | Mercy Kiologwe
Designation: |  | SHEQ Manager

## Approval Cover note
Risk Assessment Method Statement
Project Name: | HTT ACTIVE EQUIPMENT AUDIT
Company Name: | GNC Solutions Ltd
Number of sites | 155
Casual Laborers Required?[Yes/No] | No
Lifting Plan required? [Yes/No] | No
Site details:
Number of sites | Site ID | Site Name | Region
1 | DAR104 | Mpiji | Dar es Salaam
1 | DAR107 | Ubungo_Garage | Dar es Salaam
1 | DAR140 | Kiluvya | Dar es Salaam
1 | DAR161 | Kibamba | Dar es Salaam
1 | 1645 | Goba Center | Dar es Salaam
1 | DAR146 | Mabibo | Dar es Salaam
1 | DA0371 | Kibamba_Ondogo_VTZ | Dar es Salaam
1 | DAR256 | Mabibo-Loyola | Dar es Salaam
1 | 1125 | Goba_Kunguru | Dar es Salaam
1 | DAR194 | Madale | Dar es Salaam
1 | DAR519 | Tabata Darwest | Dar es Salaam
1 | DAR057 | Luguruni | Dar es Salaam
1 | DAR247 | Tabata Liwiti | Dar es Salaam
1 | DAR589 | Mikang'a | Dar es Salaam
1 | 1296 | Boko | Dar es Salaam
1 | DAR159 | Tabata_Ch_Gombe | Dar es Salaam
1 | DAR242 | Bunju Ccm | Dar es Salaam
1 | DAR253 | Kwa Yusufu | Dar es Salaam
1 | DAR524 | Swai_Kisukulu | Dar es Salaam
1 | 1078 | Bunju | Dar es Salaam
1 | DAR374 | Mbezi Makondeni Replacement | Dar es Salaam
1 | DAR518 | Segerea_Shule | Dar es Salaam
1 | DAR664 | Mbweni_JKT | Dar es Salaam
1 | DAR085 | Mbezi_Luis(Mbezi_Kimara) | Dar es Salaam
1 | DAR310 | Tabata_Migombani | Dar es Salaam
1 | 1556 | Freedom street | Dar es Salaam
1 | DAR628 | Tegeta _Mtakuja | Dar es Salaam
1 | DAR025 | Temboni | Dar es Salaam
1 | DAR105 | Mtongani | Dar es Salaam
1 | DAR651 | KWAKIJOGOO | Dar es Salaam
1 | DAR304 | Kilongawima | Dar es Salaam
1 | DAR523 | Kwa_Biesta | Dar es Salaam
1 | DAR052 | Kimara | Dar es Salaam
1 | DAR149 | Kimara North | Dar es Salaam
1 | 1063 | Ukonga | Dar es Salaam
1 | 1303 | Salasala | Dar es Salaam
1 | DAR547 | Kinzudi | Dar es Salaam
1 | DAR642 | ULONGONI-B | Dar es Salaam
1 | 1187 | Golani | Dar es Salaam
1 | DAR625 | Mavurunza G5 | Dar es Salaam
1 | 1395 | Ulongali | Dar es Salaam
1 | 1105 | Mbezi_Industrial | Dar es Salaam
1 | DAR142 | Pugu Mnadani | Dar es Salaam
1 | 1183 | Kilungule | Dar es Salaam
1 | 1704 | Mbezi_RC (Hekima_Street) | Dar es Salaam
1 | DAR014 | Mbezi | Dar es Salaam
1 | DAR119 | Ilala_Bomani | Dar es Salaam
1 | DAR122 | Ubungo_Rubada | Dar es Salaam
1 | DAR202 | Kawe Mzimuni | Dar es Salaam
1 | DAR217 | Kekomwanga B | Dar es Salaam
1 | DAR120 | Mlimani_City | Dar es Salaam
1 | DAR126 | Kunduchi Beach | Dar es Salaam
1 | DAR136 | Keko Mwanga | Dar es Salaam
1 | DAR368 | Radio Maria | Dar es Salaam
1 | 6385 | Kihesa_Sokoni | Iringa
1 | LND225 | Kilwa_Kisagi | Lindi
1 | 6050 | 40-Lindi_Town | Lindi
1 | 6387 | Mkwawa | Iringa
1 | 6461 | Changarawe_2 | Iringa
1 | 6026 | Changarawe | Iringa
1 | IRI011 | Mgololo Tx | Iringa
1 | 5526 | Mbaramaziwa | Iringa
1 | MBY024 | Mbarali | Mbeya
1 | MBY013 | Chimala | Mbeya
1 | MBY041 | Isyesye | Mbeya
1 | 6003 | Mbeya_East | Mbeya
1 | MTR007 | Mikindani | Mtwara
1 | MBY039 | Sae(Mkwawa) | Mbeya
1 | DAR573 | Kurasini_Polisi | Dar es Salaam
1 | DAR267 | Makumbusho | Dar es Salaam
1 | DAR220 | Kawa-Desuce | Dar es Salaam
1 | DAR595 | Feza | Dar es Salaam
1 | DAR051 | Mwananyamala | Dar es Salaam
1 | DAR232 | Kwa Temba | Dar es Salaam
1 | 1216 | Mtambani | Dar es Salaam
1 | 1011 | Changombe | Dar es Salaam
1 | DAR018 | Kinondoni | Dar es Salaam
1 | DAR091 | Sigara | Dar es Salaam
1 | DAR248 | Mtambani | Dar es Salaam
1 | 1094 | Tandale_Primary | Dar es Salaam
1 | 1157 | Ndugumbi | Dar es Salaam
1 | DAR197 | Chiwanda | Dar es Salaam
1 | DAR538 | Mianzini | Dar es Salaam
1 | DAR363 | Mwembe Umbea | Dar es Salaam
1 | DAR344 | Vituka Machimbo | Dar es Salaam
1 | DAR145 | Mikoroshini | Dar es Salaam
1 | 1180 | ChemChem | Dar es Salaam
1 | DAR223 | Lumo | Dar es Salaam
1 | 1131 | Yombo_Machimbo | Dar es Salaam
1 | DAR060 | Vituka | Dar es Salaam
1 | DAR348 | Mtoni Chaurembo | Dar es Salaam
1 | DAR457 | Bank Club | Dar es Salaam
1 | 1160 | Nasako | Dar es Salaam
1 | DAR358 | Mbagalasnake | Dar es Salaam
1 | DAR562 | Mandazi Road | Dar es Salaam
1 | DAR227 | Kibonde Maji | Dar es Salaam
1 | DAR561 | Zakhem Jeshini | Dar es Salaam
1 | DAR356 | Kiburungwa | Dar es Salaam
1 | DAR404 | Mbagala Vioo | Dar es Salaam
1 | DAR345 | Mbagala_Tanita | Dar es Salaam
1 | DAR571 | Mianzini B | Dar es Salaam
1 | DAR246 | Kongowe Mzinga | Dar es Salaam
1 | DAR570 | Mbagala Mponda | Dar es Salaam
1 | 1009 | Ocean_Road | Dar es Salaam
1 | DAR121 | Maweni | Dar es Salaam
1 | 1117 | Kigamboni | Dar es Salaam
1 | DAR059 | Yombodovya | Dar es Salaam
1 | 1083 | Mazengo_Street | Dar es Salaam
1 | DAR459 | Kwa Mapambano | Dar es Salaam
1 | 1203 | Kipunguni2 | Dar es Salaam
1 | DAR493 | Saku | Dar es Salaam
1 | DAR402 | Nyeburu | Dar es Salaam
1 | DAR532 | Chakenge | Dar es Salaam
1 | 1121 | Kipunguni | Dar es Salaam
1 | DAR712 | MVUTI | Dar es Salaam
1 | DAR165 | Majohe | Dar es Salaam
1 | DAR155 | Kwembe | Dar es Salaam
1 | LND008 | Nyangao | Lindi
1 | MTR005 | Tandahimba | Mtwara
1 | MB0182 | Ituha_VTZ | Mbeya
1 | MB0186 | Iduda_VTZ | Mbeya
1 | MBY040 | Ndaga Replacement | Mbeya
1 | MBY018 | Kiwira | Mbeya
1 | 6248 | Kiwira_Prison | Mbeya
1 | MBY048 | Lwangwa | Mbeya
1 | MBY031 | Kiwira Coal Mine | Mbeya
1 | 6039 | Kasumulo | Mbeya
1 | MBY074 | Iyunga | Mbeya
1 | 5506 | Iganzo | Mbeya
1 | MBY016 | Karuwe_Hill | Mbeya
1 | 6442 | Songwe_Airport | Mbeya
1 | 6110 | Mkwajuni_Chunya | Mbeya
1 | 6338 | NewSaza_Mine | Songwe
1 | 6305 | 45-Nanyanga | Mtwara
1 | 6306 | 44-Mkunya | Mtwara
1 | 6311 | 37-Jidah | Mtwara
1 | 6249 | NewLupatingatinga | Mbeya
1 | MBY020 | Mahenje_Mbozi | Songwe | -3.8193
1 | MBY051 | Igamba | Songwe | -9.209
1 | 6299 | 36-Lukuledi | Mtwara | -2.5206
1 | LND235 | Kazamoyo | Lindi | -2.0823
1 | 6449 | Vwawa_Mbimba | Songwe | -10.6904
1 | 6381 | Ilembo | Songwe | -10.3952
1 | 6021 | Tunduma | Songwe | -3.6659
1 | 6391 | Tunduma_Center (Msasani Tunduma) | Songwe | -5.4237
1 | 6334 | Tunduma_Kilimahewa | Songwe | -5.0209
1 | LND010 | Nachingwea | Lindi | -5.4894
1 | LND014 | Nammanga_Hill | Lindi | -4.7883
1 | 6304 | 35-Michiga | Mtwara | -4.3462
1 | 6389 | Tunduma3_Cap (Mkombozi Tunduma) | Songwe | -5.3021
1 | 6421 | Itambula | Songwe | -5.0097
1 | 6078 | NewIleje | Songwe | -5.2057
1 | 6418 | Isongole | Songwe | -4.7874
1 | 6524 | CHIPAKA-B | Songwe | -4.8337
1 | MB0055 | Chitete_VTZ | Mbeya | -4.8508
Prepared by: GNC Solutions Ltd |  | Signature: | Date: 24September2024
Name: | Michael Ngido
Designation: | SHEQ Manager
Reviewed and Approved by: GNC Solutions Ltd |  | Signature: | Date: 24September2024
Name: | Onesmo Swalo
Designation: | Project Manager
Approved by Project Manager [Helios Towers] |  | Signature: | Date:
Name: | Benjamin Michael
Designation: | Project Manager
Approved by SHEQ Manager [Helios Towers] |  | Signature: | Date:
Name: | Mercy Lyimo
Designation: | SHEQ Manager